## Summary
Project Keystone · Brennard Foods procurement transformation tracker
Last updated 1 October 2026 (for the steerco). Illustrative example · Fictional company and sample data
Measure | Value
Run-rate savings target ($k) | 6000
Confirmed run-rate savings ($k)
Share of target confirmed
Workstreams Green
Workstreams Amber
Workstreams Red
Average % complete
Open risks

## Workstreams
ID | Workstream | Owner | Status | % complete | Due date | Confirmed run-rate savings ($k) | Latest note
WS1 | Spend baseline | Priya Nair | Green | 100% | 2026-08-14 | 0 | Complete; baseline signed off by finance
WS2 | Category wave 1: packaging | Daniel Ortiz | Green | 100% | 2026-09-30 | 1450 | Contracts signed with 3 suppliers
WS3 | Category wave 2: logistics | Daniel Ortiz | Green | 85% | 2026-10-30 | 1250 | Final carrier negotiations under way
WS4 | Category wave 3: indirect spend | Tom Brooks | Green | 60% | 2026-12-15 | 900 | Facilities and IT categories in sourcing
WS5 | Supplier consolidation | Grace Liu | Green | 55% | 2026-11-13 | 0 | 212 suppliers mapped; 14 exit contracts drafted
WS6 | Procure-to-pay (P2P) rollout | Sam Patel | Amber | 40% | 2027-01-15 | 0 | Integration testing started; go-live 15 Jan
WS7 | Tail-spend pilot | Grace Liu | Green | 20% | 2026-12-31 | 0 | Pilot design ready; awaiting steerco approval
WS8 | Change management and training | Priya Nair | Green | 35% | 2027-01-29 | 0 | Training plan drafted for 340 buyers

## Risks
ID | Risk | Impact | Likelihood | Owner | Status | Mitigation
R1 | Business units keep buying off-contract after go-live | High | Medium | Sam Patel | Open | Block off-contract POs in P2P; monthly compliance report
R2 | Packaging supplier passes through resin price increase | Medium | Medium | Daniel Ortiz | Open | Index clause negotiated in wave 1 contracts
R3 | Finance cannot validate savings fast enough for quarter close | Medium | Low | Priya Nair | Open | Weekly savings validation slot with FP&A
R4 | Union consultation delays warehouse supplier changes | Low | Low | Grace Liu | Open | Consultation scheduled for October