## Slide 1
Project Keystone
Brennard Foods procurement transformation
Steering committee · 1 October 2026
Illustrative example · Fictional company and sample data

## Slide 2
PROJECT KEYSTONE · STEERING COMMITTEE · 1 OCTOBER 2026
Keystone is on track: 7 of 8 workstreams are green and $3.6M of the $6.0M savings target is confirmed
Illustrative example · Fictional company and sample data
2
Overall status: GREEN · Confirmed run-rate savings $3,600k (60% of target) · Next steerco 5 November 2026
Workstream | Owner | Status | % complete | Due | Savings ($k)
Spend baseline | Priya Nair | Green | 100% | 14 Aug 2026 | –
Category wave 1: packaging | Daniel Ortiz | Green | 100% | 30 Sep 2026 | 1,450
Category wave 2: logistics | Daniel Ortiz | Green | 85% | 30 Oct 2026 | 1,250
Category wave 3: indirect spend | Tom Brooks | Green | 60% | 15 Dec 2026 | 900
Supplier consolidation | Grace Liu | Green | 55% | 13 Nov 2026 | –
Procure-to-pay (P2P) rollout | Sam Patel | Amber | 40% | 15 Jan 2027 | –
Tail-spend pilot | Grace Liu | Green | 20% | 31 Dec 2026 | –
Change management and training | Priya Nair | Green | 35% | 29 Jan 2027 | –

## Slide 3
PROJECT KEYSTONE · STEERING COMMITTEE · 1 OCTOBER 2026
The committee is asked to approve the tail-spend pilot in two regions; supplier consolidation stays on plan for 13 November
Illustrative example · Fictional company and sample data
3
Decision requested today
• Approve a tail-spend pilot in the Midlands and North regions from 20 October
• Scope: purchases under $5k, 38% of transactions but 4% of spend
• Budget within the existing programme envelope
Next steps before 5 November
• Finance to validate logistics savings (wave 2)
• Legal review of 14 supplier exit contracts by 13 November
• P2P integration testing; go-live 15 January 2027
• Indirect spend (wave 3): facilities and IT categories to sourcing
Top risks
R1 Business units keep buying off-contract after go-live (impact High, likelihood Medium; owner Sam Patel)
R2 Packaging supplier passes through resin price increase (impact Medium, likelihood Medium; owner Daniel Ortiz)
R3 Finance cannot validate savings fast enough for quarter close (impact Medium, likelihood Low; owner Priya Nair)