## Slide 1
PROJECT ATLAS · ERP MIGRATION · WEEK 18
Status update
Illustrative example · Fictional company and sample data · Test task 3 of 3 (PowerPoint)
1
• Data migration test cycle 2 completed 14 Jul; 3.1% of customer records failed validation
• Integration testing with the warehouse system started 21 Jul; 62% of test scripts passed so far
• Training materials drafted for finance and procurement users
• Vendor change: lead functional consultant replaced on 18 Jul
• Budget: $2.31M spent of $3.40M (68%) with 72% of the timeline elapsed
• Cutover rehearsal 1 moved from 28 Jul to 11 Aug
• Risk: the August month-end close overlaps the go-live window
• Decision needed: see slide 4

## Slide 2
PROJECT ATLAS · ERP MIGRATION · WEEK 18
Timeline
Illustrative example · Fictional company and sample data · Test task 3 of 3 (PowerPoint)
2
Milestone | Planned | Forecast | Status
Design sign-off | 15 Mar | 15 Mar | Done
Build complete | 30 May | 6 Jun | Done
System integration testing | 21 Jul–1 Aug | 21 Jul–15 Aug | In progress
Cutover rehearsal 1 | 28 Jul | 11 Aug | Moved
Go-live | 3 Aug | 24 Aug (proposed) | At risk

## Slide 3
PROJECT ATLAS · ERP MIGRATION · WEEK 18
Budget
Illustrative example · Fictional company and sample data · Test task 3 of 3 (PowerPoint)
3
Chart: 
| Mar | Apr | May | Jun | Jul
Planned spend ($k) | 400 | 460 | 480 | 470 | 450
Actual spend ($k) | 380 | 450 | 470 | 500 | 510
• Spend to date: $2.31M vs $2.26M planned
• Total budget: $3.40M
• June and July ran above plan because of extra test resources
• A three-week go-live delay adds an estimated $85k

## Slide 4
PROJECT ATLAS · ERP MIGRATION · WEEK 18
Next steps
Illustrative example · Fictional company and sample data · Test task 3 of 3 (PowerPoint)
4
• Fix the customer-record validation failures before test cycle 3 (data team, by 1 Aug)
• Complete integration testing with the warehouse system (by 15 Aug)
• Run cutover rehearsal 1 on 11 Aug
• Finalise the training schedule with finance and procurement
• Onboard the replacement functional consultant
• Steering committee: approve moving go-live from 3 Aug to 24 Aug, so it clears the August close (cost about $85k)