## Slide 1
Project progress report
Customer portal rollout
Week 6 of 10 · 25 September 2026
Filled example with fictional data
Deckary
Notes: Original Deckary reporting template. All company names, events, dates and numbers in the filled example are illustrative, not customer results. Replace them with approved reporting data. Native PowerPoint tables and chart data remain editable.

## Slide 2
The launch date depends on a QA decision
Customer portal rollout. Reporting period: 21–25 September 2026.
Illustrative example · Fictional company and sample data · Deckary
2
Area | Status | Evidence / implication
Schedule | At risk | Launch on 23 Oct depends on QA capacity
Scope | On track | 12 of 20 work packages complete (60%)
Budget | At risk | $252k forecast versus $240k approved
Decision | Due 28 Sep | Approve $12k for additional QA capacity
Overall status is at risk because the launch and forecast budget depend on the pending approval.
Notes: Original Deckary template, not sourced customer information. All names and numbers are fictional examples.
Overall status is at risk because the launch and forecast budget depend on the pending approval.

## Slide 3
Integration is complete and QA begins next week
Compare the agreed baseline with the current forecast
Illustrative example · Fictional company and sample data · Deckary
3
Milestone | Baseline | Forecast / actual | Owner
Discovery sign-off | 28 Aug | 28 Aug · complete | Product lead
Integration complete | 25 Sep | 25 Sep · complete | Tech lead
QA sign-off | 9 Oct | 16 Oct · at risk | QA lead
Customer launch | 23 Oct | 23 Oct · at risk | Sponsor
QA has a seven-day forecast delay. The launch date remains possible only if additional capacity clears the dependency.
Notes: Original Deckary template, not sourced customer information. All names and numbers are fictional examples.
QA has a seven-day forecast delay. The launch date remains possible only if additional capacity clears the dependency.

## Slide 4
Spend is below plan while delivery risk remains
Cumulative project spend, USD thousands
Illustrative example · Fictional company and sample data · Deckary
4
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6
Actual | 18 | 40 | 65 | 90 | 110 | 132
Planned | 20 | 45 | 70 | 95 | 120 | 144
Week 6 spend is $132k versus $144k planned. Underspend alone does not show delivery is on track. Forecast final cost is $252k.
Notes: Original Deckary template, not sourced customer information. All names and numbers are fictional examples.
Week 6 spend is $132k versus $144k planned. Underspend alone does not show delivery is on track. Forecast final cost is $252k.
Chart source data: {"type":"line","categories":["W1","W2","W3","W4","W5","W6"],"series":[{"name":"Actual","values":[18,40,65,90,110,132]},{"name":"Planned","values":[20,45,70,95,120,144]}],"format":"$0\"k\""}

## Slide 5
Forecast cost exceeds budget by $12k
USD thousands. Actual to date plus remaining estimate equals forecast.
Illustrative example · Fictional company and sample data · Deckary
5
Workstream | Budget | Actual | Remaining | Forecast
Discovery | 40 | 24 | 16 | 40
Build | 120 | 72 | 60 | 132
QA | 48 | 24 | 24 | 48
Rollout | 32 | 12 | 20 | 32
Total | 240 | 132 | 120 | 252
Forecast variance = $252k − $240k = $12k (5%). Additional QA capacity supports build verification and is charged to the build workstream.
Notes: Original Deckary template, not sourced customer information. All names and numbers are fictional examples.
Forecast variance = $252k − $240k = $12k (5%). Additional QA capacity supports build verification and is charged to the build workstream.

## Slide 6
Test environment access blocks two work packages
Current blockers need a dated resolution, not only a status label
Illustrative example · Fictional company and sample data · Deckary
6
Blocker / risk | Impact | Action / owner / due
Test environment access | Two packages cannot begin QA | IT grants access / Tech lead / 28 Sep
QA capacity gap | Forecast sign-off moves to 16 Oct | Confirm contractor / Sponsor / 28 Sep
Late scope requests | Could increase release workload | Freeze changes / Product lead / 30 Sep
Distinguish a current blocker from a future risk. Escalate overdue actions at the next sponsor meeting.
Notes: Original Deckary template, not sourced customer information. All names and numbers are fictional examples.
Distinguish a current blocker from a future risk. Escalate overdue actions at the next sponsor meeting.

## Slide 7
Approval on 28 September protects the launch plan
Accountability for the next reporting period
Illustrative example · Fictional company and sample data · Deckary
7
Action / decision | Owner | Due / acceptance
Approve $12k budget increase | Sponsor | 28 Sep / cap becomes $252k
Confirm QA contractor capacity | QA lead | 29 Sep / booking confirmed
Complete regression test cycle | Tech lead | 2 Oct / critical defects triaged
Issue next progress report | Project manager | 2 Oct / forecasts refreshed
If the sponsor declines the increase, replan the QA scope and launch date. Record the actual decision rather than assuming approval.
Notes: Original Deckary template, not sourced customer information. All names and numbers are fictional examples.
If the sponsor declines the increase, replan the QA scope and launch date. Record the actual decision rather than assuming approval.