## Project Budget
Category | Description | Estimated Cost | Actual Cost | Variance ($) | Variance (%) | Status
Pre-Engagement
Strategy & Planning | Consulting layout, workspace layout, dining area plans | 45000 | 47500 | -2500 | -5.556% | Complete
Research & Analysis | Structural, mechanical, electrical engineering | 28000 | 26800 | 1200 | 4.286% | Complete
Compliance & Approvals | Building permits, health dept, liquor license fees | 18000 | 19200 | -1200 | -6.667% | Complete
Market Research | Site survey, geotechnical report | 5500 | 5500 | 0 | 0% | Complete
Project Management | Owner's rep / project manager fees | 35000 | 33000 | 2000 | 5.714% | Complete
Pre-Engagement Subtotal |  | 131500 | 132000 | -500 | -0.3802%
Infrastructure Setup
Legacy System Decommissioning | Demo of existing structures / interior strip-out | 32000 | 38500 | -6500 | -20.31% | Complete
Data Migration & Integration | Site grading, trenching, compaction | 18000 | 17200 | 800 | 4.444% | Complete
Network & Connectivity | Water, sewer, gas, electric service connections | 25000 | 24000 | 1000 | 4% | Complete
Office Space & Facilities | Lot paving, striping, outdoor landscaping | 22000 | 21500 | 500 | 2.273% | Complete
Infrastructure Setup Subtotal |  | 97000 | 101200 | -4200 | -4.33%
Core Systems & Architecture
Foundation Systems | Footings, slab, waterproofing | 55000 | 58000 | -3000 | -5.455% | Complete
Core Infrastructure Build | Wood/steel framing, load-bearing walls | 72000 | 69500 | 2500 | 3.472% | Complete
System Security & Protection | Roof structure, membrane, insulation | 28000 | 27000 | 1000 | 3.571% | Complete
Core Systems & Architecture Subtotal |  | 155000 | 154500 | 500 | 0.3226%
Technology & Operations
Climate & Environment Control | Exhaust fans, work area HVAC, ventilation | 65000 | 68000 | -3000 | -4.615% | Complete
Power & Electrical Systems | Panel, wiring, outlets, lighting circuits | 42000 | 40500 | 1500 | 3.571% | Complete
Water & Utility Systems | Water lines, drains, grease trap, gas lines | 38000 | 36000 | 2000 | 5.263% | Complete
Safety & Risk Management | Sprinklers, fire suppression system | 22000 | 22000 | 0 | 0% | Complete
Technology & Operations Subtotal |  | 167000 | 166500 | 500 | 0.2994%
Office & Workspace Setup
Flooring & Foundation Materials | Commercial flooring, work areas, restrooms | 35000 | 33000 | 2000 | 5.714% | Complete
Walls & Partitioning | Drywall, paint, accent walls, ceiling treatment | 28000 | 25500 | 2500 | 8.929% | In Progress
Facilities & Common Areas | Fixtures, tile, ADA compliance | 18000 | 12000 | 6000 | 33.33% | In Progress
Access & Security Hardware | Interior doors, entry door, hardware | 12000 |  |  |  | Not Started
Custom Furniture & Millwork | Bar top, wainscoting, custom woodwork | 45000 | 18000 | 27000 | 60% | In Progress
Office & Workspace Setup Subtotal |  | 138000 | 88500 | 49500 | 35.87%
Office Equipment & Technology
IT Hardware & Servers | Primary equipment and machinery | 48000 | 48000 | 0 | 0% | Complete
Data Storage & Backup Systems | Storage units and climate-controlled systems | 35000 | 35000 | 0 | 0% | Complete
Productivity Tools & Software | Prep tables, mixers, food processors, sinks | 15000 |  |  |  | Not Started
Maintenance & Support Equipment | Cleaning and waste equipment | 12000 |  |  |  | Not Started
Office Supplies & Accessories | Tools, accessories, and storage | 8000 |  |  |  | Not Started
Office Equipment & Technology Subtotal |  | 118000 | 83000 | 35000 | 29.66%
Furniture & Fixtures
Office Furniture & Seating | Tables, chairs, booths, bar stools | 42000 |  |  |  | Not Started
Lighting & Fixtures | Pendants, sconces, ambient lighting | 18000 |  |  |  | Not Started
Management Software | Terminals, printers, management display | 15000 |  |  |  | Not Started
Audio/Visual Systems | Speakers, amplifier, background music setup | 5500 |  |  |  | Not Started
Signage & Branding | Exterior sign, menu boards, wayfinding | 12000 |  |  |  | Not Started
Furniture & Fixtures Subtotal |  | 92500 | 0 | 92500 | 100%
Technology & Security
Security & Access Control | Cameras, alarm, access control | 8000 |  |  |  | Not Started
IT Infrastructure & Networking | Wi-Fi, cabling, office computer | 6000 |  |  |  | Not Started
Communications & Phone System | Business phone / reservation system | 3500 |  |  |  | Not Started
Technology & Security Subtotal |  | 17500 | 0 | 17500 | 100%
Professional Services
Insurance & Liability | Builder's risk, general liability during construction | 9500 | 9500 | 0 | 0% | Complete
Legal & Compliance | Lease review, contracts, entity formation | 12000 | 11000 | 1000 | 8.333% | Complete
Accounting & Finance Setup | Setup, bookkeeping system, tax registration | 5000 | 4800 | 200 | 4% | Complete
Marketing & Brand Development | Logo, menu design, website, pre-opening marketing | 25000 | 15000 | 10000 | 40% | In Progress
Team Training & Onboarding | Staff hiring, training, soft opening costs | 18000 |  |  |  | Not Started
Professional Services Subtotal |  | 69500 | 40300 | 29200 | 42.01%
GRAND TOTAL (before contingency) |  | 986000 | 766000 | 220000 | 22.31%
Contingency (%) | Percentage of total estimated cost | 10%
Contingency Amount |  | 98600
PROJECT TOTAL (with contingency) |  | 1084600 | 766000 | 318600 | 29.37%

## Cost Tracker
Date | Vendor / Payee | Category | Description | Amount | Payment Method | Receipt # | Notes | Running Total
2025-01-05 | State Farm Business | Professional Services | Builder's risk insurance - 12 month | 9500 | ACH | POL-8801 | Covers engagement period | 9500
2025-01-08 | Miller Architecture Group | Pre-Engagement | Architectural design - deposit (50%) | 22500 | Wire Transfer | INV-1001 | Initial planning phase | 32000
2025-01-15 | Greenfield Engineering | Pre-Engagement | Structural engineering assessment | 26800 | Check | INV-1002 | Delivered ahead of schedule | 58800
2025-01-20 | Chen & Associates Law | Professional Services | Lease review & entity formation | 11000 | Wire Transfer | INV-8802 | LLC formation + contract nego | 69800
2025-01-22 | City of Portland | Pre-Engagement | Building permits & health dept fees | 12200 | Check | PMT-0301 | Includes compliance review | 82000
2025-01-28 | GeoTest Labs | Pre-Engagement | Site survey & geotechnical report | 5500 | Credit Card | REC-4401 |  | 87500
2025-02-01 | Portland CPA Group | Professional Services | Accounting setup & tax registration | 4800 | Check | INV-8803 | QuickBooks setup included | 92300
2025-02-05 | Miller Architecture Group | Pre-Engagement | Architectural design - final payment | 25000 | Wire Transfer | INV-1003 | Revised workspace layout | 117300
2025-02-10 | City of Portland | Pre-Engagement | Liquor license application fee | 7000 | Check | PMT-0302 | Full-service engagement | 124300
2025-02-15 | Cascade PM Services | Pre-Engagement | Project management - Month 1 | 16500 | ACH | INV-2201 |  | 140800
2025-02-28 | Cascade PM Services | Pre-Engagement | Project management - Month 2 | 16500 | ACH | INV-2202 |  | 157300
2025-03-03 | Pacific Legacy System Decommissioning Co | Infrastructure Setup | Interior strip-out & demolition | 28500 | Check | INV-3301 | Includes removal & cleanup | 185800
2025-03-10 | Pacific Legacy System Decommissioning Co | Infrastructure Setup | Asbestos abatement - change order | 10000 | Check | INV-3302 | Unexpected infrastructure issue | 195800
2025-03-15 | Willamette Excavation | Infrastructure Setup | Grading & trenching | 17200 | Check | INV-3303 |  | 213000
2025-03-20 | Portland Water Bureau | Infrastructure Setup | Water & sewer connection fees | 14000 | Wire Transfer | PMT-0501 | Connection fees + provisioning | 227000
2025-03-22 | NW Gas & Electric | Infrastructure Setup | Gas & electric service upgrade | 10000 | Wire Transfer | PMT-0502 | Enterprise power distribution | 237000
2025-03-28 | Summit Paving | Infrastructure Setup | Parking lot repaving & landscaping | 21500 | Check | INV-3305 | Multiple workstations + setup | 258500
2025-04-02 | Bedrock Foundation Systemss Inc | Core Systems & Architecture | Foundation Systems - footings & slab pour | 58000 | Wire Transfer | INV-4401 | Reinforced for server room | 316500
2025-04-18 | Ironworks Structural | Core Systems & Architecture | Steel framing & load-bearing walls | 42000 | Wire Transfer | INV-4402 | Phase 1 - core infrastructure | 358500
2025-05-01 | Ironworks Structural | Core Systems & Architecture | Framing completion & inspection | 27500 | Wire Transfer | INV-4403 | Passed systems inspection | 386000
2025-05-12 | Summit System Security & Protection NW | Core Systems & Architecture | Commercial roofing - TPO membrane | 27000 | Check | INV-4404 | 5-year warranty | 413000
2025-05-15 | Ember Creative Agency | Professional Services | Logo, branding & website - Phase 1 | 10000 | Wire Transfer | INV-8804 | Brand identity package | 423000
2025-05-20 | Cascade Climate & Environment Controls | MEP | Kitchen exhaust hood & make-up air | 38000 | Wire Transfer | INV-5501 | Enhanced capacity per requirements | 461000
2025-05-28 | Cascade Climate & Environment Controls | MEP | Dining area HVAC - mini splits | 30000 | Wire Transfer | INV-5502 | 4-zone system | 491000
2025-06-05 | Bright Spark Electric | MEP | Full electrical rough-in & panel | 40500 | Check | INV-5503 | Enterprise distribution + backup | 531500
2025-06-12 | Flow Right Water & Utility Systems | MEP | Water & Utility Systems rough-in, grease trap, gas | 36000 | Check | INV-5504 | Advanced waste management system | 567500
2025-06-18 | Pacific Fire Protection | MEP | Sprinklers & Ansul system install | 22000 | Check | INV-5505 | Office + collaboration areas | 589500
2025-07-01 | Artisan Tile & Stone | Office & Workspace Setup | Kitchen & restroom tile | 18000 | Check | INV-6601 | Commercial-grade surfaces | 607500
2025-07-08 | Artisan Tile & Stone | Office & Workspace Setup | Dining area hardwood flooring | 15000 | Check | INV-6602 | Premium hardwood | 622500
2025-07-10 | Consulting Depot | Office Equipment & Technology | Range, oven, grill, fryers | 48000 | Financing | PO-7701 | Financing program | 670500
2025-07-15 | Pro Drywall NW | Office & Workspace Setup | Drywall, taping & accent walls | 25500 | Check | INV-6603 | Includes accent wall | 696000
2025-07-20 | Ember Creative Agency | Professional Services | Menu design & social media setup | 5000 | Credit Card | INV-8805 | Launch marketing campaign | 701000
2025-07-22 | Rose City Water & Utility Systems | Office & Workspace Setup | Restroom fixtures & tile - deposit | 12000 | Credit Card | INV-6604 | ADA compliant | 713000
2025-07-28 | Heritage Woodworks | Office & Workspace Setup | Bar top - walnut slab - deposit | 18000 | Wire Transfer | INV-6605 | Custom reception desk | 731000
2025-08-01 | Arctic Commercial Data Storage & Backup Systems | Office Equipment & Technology | commercial storage, freezer, reach-ins | 35000 | Wire Transfer | INV-7702 | Installed & operational | 766000

## Dashboard
Consulting Project Budget — Dashboard
Key Performance Indicators |  |  | Budget Health
Total Budget (with Contingency) | 1084600 |  | Total Estimated (before contingency) | 986000
Total Spent to Date | 766000 |  | Total Actual (before contingency) | 766000
Budget Remaining | 318600 |  | Overall Variance ($) | 220000
% of Budget Spent | 70.63% |  | Overall Variance (%) | 22.31%
Contingency Remaining | 98600 |  | Contingency (%) | 10%
Chart Source Data
Category | Estimated | Actual | Date | Cumulative Spend
Pre-Engagement | 131500 | 132000 | 2025-01-05 | 9500
Infrastructure Setup | 97000 | 101200 | 2025-01-08 | 32000
Core Systems & Architecture | 155000 | 154500 | 2025-01-15 | 58800
MEP | 167000 | 166500 | 2025-01-20 | 69800
Office & Workspace Setup | 138000 | 88500 | 2025-01-22 | 82000
Office Equipment & Technology | 118000 | 83000 | 2025-01-28 | 87500
FF&E | 92500 | 0 | 2025-02-01 | 92300
Technology & Security | 17500 | 0 | 2025-02-05 | 117300
Professional Services | 69500 | 40300 | 2025-02-10 | 124300
|  |  | 2025-02-15 | 140800
Budget Gauge | Amount |  | 2025-02-28 | 157300
Spent | 766000 |  | 2025-03-03 | 185800
Remaining | 318600 |  | 2025-03-10 | 195800
|  |  | 2025-03-15 | 213000
|  |  | 2025-03-20 | 227000
|  |  | 2025-03-22 | 237000
|  |  | 2025-03-28 | 258500
|  |  | 2025-04-02 | 316500
|  |  | 2025-04-18 | 358500
|  |  | 2025-05-01 | 386000
|  |  | 2025-05-12 | 413000
|  |  | 2025-05-15 | 423000
|  |  | 2025-05-20 | 461000
|  |  | 2025-05-28 | 491000
|  |  | 2025-06-05 | 531500
|  |  | 2025-06-12 | 567500
|  |  | 2025-06-18 | 589500
|  |  | 2025-07-01 | 607500
|  |  | 2025-07-08 | 622500
|  |  | 2025-07-10 | 670500
|  |  | 2025-07-15 | 696000
|  |  | 2025-07-20 | 701000
|  |  | 2025-07-22 | 713000
|  |  | 2025-07-28 | 731000
|  |  | 2025-08-01 | 766000